## Module descriptions
Parts | Elements | Functions | Description | Note | Phase | Language | Status | Issues
Hardware | Design | Solidwork | * Draw the robot with: ** 2 Motors ** 1 Covers ** 2 Wheels ** 1 multi-direction wheel ** … |  | 1 |  | In process
|  | Circuits | * power and communication ** … |  | 1 |  | In process | Chưa thiết kế được vì chưa có tiện
| Modules | STM32F407 | * It is the master for Robot |  | 1 |  | Review | Đã có
|  | STM32F411 | * It is drivers for motors * Include 2 KIT | It's Mr.Kien | 1 |  | Review | Chưa mượn thầy
|  | HC06 | * Use to communicate with PC by bluetooth | Only test interaction with PC on phase 1 | 1 |  | In process | Chưa có tiền mua. Và chưa cần thiết
Firmware | Modules | PWM | * Generate pulse to control speed motor. | On only Slave | 1 | C | Review | Chưa đổ lên board để test
|  | RS485 | * Communicate between master and drivers by RS485 | On Master and slaves | 2 | C | In process | thiếu bên slave
|  | PID Algorithms | * Control speed motor base on speed error | On only Slave | 1 | C | Review | Chưa đổ lên board test
|  | Direction control | * We have 2 motors and control them independently | Depend on PWM and PID On only Master | 2 | C | Not start
|  | Reboot | * On master: load PID parameter from EEPROM and transmit drivers * On slave (driver): Wait receive data from master. And setup parameters for PID | On Master and slaves | 2 | C | Not start
|  | Bluetooth | * Communicate with PC | On only Master | 2 | C | Not start
|  | EEPROM | * Use to store PID parameters | On only Master | 2 | C | Not start
| Other | Serial Debug | * Use UART port to show log on PC's terminal | On Master and slaves | 2 | C | Not start
OS | FreeRTOS | Control task |  | On Master and slaves | 2 | C | Not start
|  | Comunication task |  | On Master and slaves | 2 | C | Not start
Software On PC | GUI | Connection Configurations | (UART) Port, Baudrate … |  | 2 | C# | Not start
|  | Select control | click button on screen or input from keyboard | Depend on Connection Configuration In order to test, set a unchanged speed. | 2 | C# | Not start
|  | Enable change speed | create a textbox and can enter speed for motors |  | 2 | C# | Not start
|  | Create a GUI to test PID | Test PID |  |  | C# | Not start | Start in 29/09/2018 and will complete in 6/10/2018 to review
|  | total | rate
| Not start | 11 | 57.89%
| In process | 4 | 21.05%
| Review | 4 | 21.05%
| Done | 0 | 0%